## Slide 1: Effective HIV and TB control in Kyrgyzstan CCM Meeting 29 January 2025

## Slide 2: General Updates
LFA: The new LFA team (KPMG) started its work November 2024.
Progress Update & Disbursement Request (Annual report to GF): Currently in under development. The usual submission deadline is February 28, but GF has communicated delays with the template. As a result, the deadline may extend.
C19RM Grant: A 6-month no-cost extension for 2025 has been confirmed by GF.
Prevention Program Review: Ongoing, expected to be finalized by February, with the tender process planned for March-April.
HIV/TB human rights component (Breaking Down Barrier): PR received GF management letter, working to address recommendations.

## Slide 3: General Updates
Migrants in the GF Program: Trainings on activities for migrants as a high-risk group for HIV and TB were conducted with GIZ’s support. Measures and activities were developed and incorporated into 2025 and 2026 ToRs.
Capacity Development of CRZ: The 2024 CDP was completed, with some activities postponed to 2025. Two new staff members joined, and all PIU positions will be re-announced. The 2025 CDP focuses on transitioning the National AIDS Center to CRZ by Q3-Q4 2025, and CRZ is working on the Framework Agreement with GF, including tax exemption.
Piloting of DHIS2 Database: The piloting began in 2024, and in 2025, all newly selected organizations will use the new system.
IBBS Among MSM and PWID: Integrated Biobehavioural Study began in January 2025, led by the AIDS Programme in collaboration with CDC.
Osh Laboratory Renovation: Renovation, completed in collaboration with GIZ and NTP, is now operational, with a formal inauguration scheduled for February 7.

## Slide 4: Programme Preliminary Results_2024_HIV Treatment Indicators
 | Target 2024 | Achievement for 2024 | % achievements
HTS-5 Percentage of people newly diagnosed with HIV who started ART | 95% | 95% | 100%
TCS-1.1⁽ᴹ⁾ Percentage of people receiving ART among all people living with HIV at the end of the reporting period | 68% | 60% | 88%
TB/HIV-6⁽ᴹ⁾ Percentage of HIV-positive patients with new and/or relapsed TB receiving ART during TB treatment | 97% | 97% | 100%
TCS-10 Percentage of pregnant women living with HIV who received antiretroviral medicine to reduce the risk of vertical transmission of HIV | 90% | 92% | 102%
TB/HIV-7.1 Percentage of people living with HIV currently enrolled on antiretroviral therapy who started TB preventive treatment (TPT) during the reporting period | 9.8% | 9.7% | 98.9%
HIV O-12 Percentage of people living with HIV and on ART who are virologically suppressed | 95% | 95% | 100%
HIV O-11 Percentage of people living with HIV who know their HIV status at the end of the reporting period | 85% | 84% | 99%

## Slide 5
Programme Preliminary Results_2024_HIV Prevention Indicators
 | Target | Achievement | %
KP-1a⁽ᴹ⁾ Percentage of MSM covered by HIV prevention programs - minimum package of services | 6760 | 8318 | 123%
HTS-3a⁽ᴹ⁾ Percentage of MSM tested for HIV during the reporting period and knowing their results | 11830 | 11819 | 99.9%
KP-6a Percentage of MSM /TG eligible for pre -exposure prophylaxis (PrEP) who received PrEP during the reporting period | 600 | 305 | 50.8%
KP-1c⁽ᴹ⁾ Percentage of SWs covered by HIV prevention programs - minimum package of services | 200 | 308 | 154%
HTS-3a⁽ᴹ⁾ Percentage of TG tested for HIV during the reporting period and knowing their results | 300 | 309 | 103%
KP-1c⁽ᴹ⁾ Percentage of SWs covered by HIV prevention programs - minimum package of services | 2325 | 1647 | 70.8%
HTS-3c⁽ᴹ⁾ Percentage of SWs tested for HIV during the reporting period and knowing their results | 6975 | 3484 | 49.9%

## Slide 6: Reasons for under achievement of some HIV indicators:
ARV Coverage (80%):
High workload of specialists and staff turnover in healthcare facilities
PrEP Indicator (50%):
Fear and anxiety about negative consequences (e.g., social isolation, harassment)
Fear of being identified, especially in rural regions, due to the requirement of presenting a passport to obtain PrEP.
Stigma and discrimination among service providers
Low community awareness regarding PrEP.
Regional differences in service coverage; for example, in the southern regions, many clients refuse PrEP due to the ongoing need to use protection (e.g., condoms).
Prevention and Testing indicators of Sex workers (70% & 50%):
In December 2023, the State Committee for National Security conducted mass raids targeting places providing sex services, leading many sex workers (SW) to leave the country or stop sex work.
Amendments to the Code of Offences and the Criminal Code of Kyrgyzstan now impose penalties for prostitution, including fines or imprisonment.
The adoption of the new NGO law in 2024 has created tensions and concerns among organizations working with key population groups (KPG).

## Slide 7: Programme Preliminary Results_2024_TB
 | Target | Achievement | %
Percentage of TB patients with DST result for at least Rifampicin | 98% | 95% | 97%
Number of people with confirmed RR-TB and/or MDR-TB notified | 1200 | 741 | 62%
Percentage of people with confirmed RR-TB and/or MDR-TB that began second-line treatment | 98% | 95% | 97%
Percentage of RR/MDR-TB patients with DST results for Fluoroquinolone among the total number of notified RR/MDR-TB patients | 85% | 89% | >100%

## Slide 8: Analysis of TB indicators for 2024:
Number of RR/MDR-TB Cases: The target was set after extensive negotiations. The project focuses on strengthening the capacity and motivation of primary health care (PHC) providers and enhancing active case finding among contacts and key affected populations.
Percentage of TB Patients with FL/SL DST Results: The performance of this indicator depends on three key factors: (1) sample quality, (2) timely and effective transportation, and (3) laboratory performance.
Percentage of People with Confirmed RR-TB and/or MDR-TB who began 2nd Line Treatment: There are no obstacles to achieving this indicator, as all TB drugs and second-line regimens (shortened or individualized) are available. A performance rate of 98-100% is expected.

## Slide 9: Delivery status as of 31 December 2024
Projects | Grant Budget | Expenses | Commit. | NEX advances | Total | Current expenses only | Budget utilization
Effective HIV and TB Control Project in KGZ | 8,503,789 | 6,229,216 | 1,911,125 | 641,367 | 8,781,708 | 73% | 103%
Global Fund COVID-19 Response | 1,304,350 | 351,164 | 631,463 | 2,593 | 985,219 | 27% | 76%

## Slide 10: Project budget Main grant
Description | 2024 | 2025 | 2026 | Total
Non-Health | 5,258,926 | 4,571,063 | 4,855,487 | 14,685,476
Health | 3,244,863 | 5,145,222 | 4,786,191 | 13,176,276
Total | 8,503,789 | 9,716,285 | 9,641,678 | 27,861,752
C19RM
Description | 2024-June 2025
Non-Health | 85,331
Health | 1,219,018
Total | 1,304,349

## Slide 11: Thank you