## Slide 1: Effective HIV and TB control in Kyrgyzstan CCM Meeting 16 May 2025

## Slide 2: General Updates
Progress Update & Disbursement Request (Annual report to GF): Submitted to donor.
C19RM Grant: Ends on 30 June 2025. An oxygen plant, diesel generator, two transformers, and 120 oxygen cylinders have been delivered and installed at Nookat Hospital. Commissioning is still on track for early June, along with training for relevant hospital staff. Purchase orders for an additional 150 oxygen cylinders, a flat panel detector for X-ray machines, and voltage regulators have been placed, with delivery expected by the end of June.
Prevention Program Review: Finalized; tender for selection of the implementors with the updated and extended ToR is almost accomplished; Series of trainings for NGOs on the extension of HIV testing among new population groups will be conducted in the upcoming 3 months.
HIV/TB human rights component (Breaking Down Barrier):With the support of CRG expert financed by GF Work Plan for 2025 is developed and approved by GF; tender for the selection of 3 organization within Matching Fund component is in process.

## Slide 3: General Updates
Capacity Development of CRZ: The 2024 CDP was completed, with some activities postponed to 2025. CDP for 2025 developed and its activities incorporated in the SR Agreement with CRZ; International expert to support CRZ capacity development continues working in 2025; 11 staff positions are filled, the selection of HIV programme specialist is in process; transition the National AIDS Center under CRZ management is expected by Q4 2025.
Piloting of DHIS2 Database: The piloting continue in 2025, all newly selected organizations uses this database, but improvement is still needed.

## Slide 4: General Updates
On the 24th of April, a letter regarding adjustments to the implementation of grant activities was received. Due to significant uncertainty about ongoing support for bilateral and multilateral health programs, including the Global Fund (GF), a set of measures to adjust implementation plans for current grants has been proposed. The implementation of certain investments should be deferred or paused until further notice from the GF.
The areas\categories to be deferred or paused:
Capital investments;
Purchase of new vehicles, IT, lab and other equipment;
Certain trainings, conferences and publications;
Surveys, studies, assessments and reviews;
Certain program management elements;
Where appropriate, certain less time-critical or essential elements of disease-specific activities.

## Slide 5: General Updates
This measure does not apply to COVID-19 Response Mechanism (C19RM) grant
Prior GF approval is now required for both material and non-material budget revisions
Expenditures inconsistent with the above guidance may be considered non-compliant
To ensure the prudent management of grant funds, upcoming disbursement amounts will
be commensurately withheld to reflect the above measures
Actions:
A meeting was held with the GF Country Team (CT) to gain more clarity.
UNDP is currently working on list of procurements and activities to be paused, in accordance with GF instructions.
Once finalized, the list will be shared with the National Programmes for discussion and agreement, after which it will be sent to the GF for further consideration and approval.

## Slide 6: Programme Results_2024_HIV Treatment Indicators
 | Target 2024 | Achievement for 2024 | % achievements
HTS-5 Percentage of people newly diagnosed with HIV who started ART | 95% | 94,4% | 99,3%
TCS-1.1⁽ᴹ⁾ Percentage of people receiving ART among all people living with HIV at the end of the reporting period | 68% | 57,45% | 79,5%
TB/HIV-6⁽ᴹ⁾ Percentage of HIV-positive patients with new and/or relapsed TB receiving ART during TB treatment | 97% | 99,12% | 101,3%
TCS-10 Percentage of pregnant women living with HIV who received antiretroviral medicine to reduce the risk of vertical transmission of HIV | 90% | 92% | 102,3%
TB/HIV-7.1 Percentage of people living with HIV currently enrolled on antiretroviral therapy who started TB preventive treatment (TPT) during the reporting period | 9.8% | 13,6% | 139%
HIV O-12 Percentage of people living with HIV and on ART who are virologically suppressed | 95% | 95% | 100%
HIV O-11 Percentage of people living with HIV who know their HIV status at the end of the reporting period | 85% | 81,7% | 96%

## Slide 7
Programme Results_2024_HIV Prevention Indicators
 | Numerator (results) | Denominator | % | Target % | % achievements
KP-1a⁽ᴹ⁾ Percentage of MSM covered by HIV prevention programs - minimum package of services (regularly) | 8 134 | 16 900 | 48% | 40% | 120%
HTS-3a⁽ᴹ⁾ Percentage of MSM tested for HIV during the reporting period and knowing their results | 11 448 | 16 900 | 67,7% | 70% | 96,7%
KP-6a Percentage of MSM /TG eligible for pre -exposure prophylaxis (PrEP) who received PrEP during the reporting period | 324 | 600 | 54% |  | 54%
KP-1c⁽ᴹ⁾ Percentage of PWID covered by HIV prevention programs - minimum package of services (regularly) | 15 999 | 25 000 | 63,3% | 60% | 106,6%
HTS-3d⁽ᴹ⁾ Percentage PWID that have received an HIV test during the reporting period and know their results | 19 121 | 25 000 | 76,5% | 75% | 102%
KP-8 Percentage of people who inject drugs receiving opioid substitution therapy | 837 | 25 000 | 3,3% | 3,2% | 104,6%
HTS-3f⁽ᴹ⁾ Number of people in prisons or other closed settings that have received an HIV test during the reporting period and know their results | 4 584 | 5 338 | 85,87% |  | 85,87%
KP-1c⁽ᴹ⁾ Percentage of SWs covered by HIV prevention programs - minimum package of services (regularly) | 2 005 | 9 300 | 21,6% | 25% | 86,3%
HTS-3c⁽ᴹ⁾ Percentage of SWs tested for HIV during the reporting period and knowing their results | 4 459 | 9,300 | 47,9% | 75% | 63,9%
KP-1b Percentage of transgender people reached with HIV prevention programs - defined package of services (regularly) | 311 | 200 | 155% |  | 155%
HTS-3b Percentage of TG that have received an HIV test during the reporting period in KPspecific programs and know their results | 328 | 300 | 109% |  | 109%

## Slide 8: Reasons for under achievement of some HIV indicators:
ARV Coverage (79,5%):
The main reason for not achieving this indicator is the significant burden associated with the management of viral hepatitis, which was added to RCCHVH&HIV since the end of 2022. This has shifted the focus of health workers to reduced attention to HIV-related issues, especially in relation to ART, in particular, ART initiation and adherence issues and stigma and discrimination by medical workers continues, which has a negative impact on PLHIV readiness to start of ART.
PrEP Indicator (54%):
Fear of negative consequences (such as social isolation, persecution, labeling) discourages people from seeking PrEP; - stigma and discrimination against MSM who came to receive the service from medical staff of AIDS centers in Bishkek.
Lack of support in achieving the indicator from community leaders in the south of the country.
Prevention activities and Testing among Sex Workers (86,3% & 63,9%):
Police raids which reduce the appeal of SWs for preventive services, including testing;
The law on NGOs, which led to the dismissal of employees and, accordingly, decrease in coverage;
Adopted amendments to the Criminal Code and the Code of Offenses in articles on administrative liability for prostitution where a fine of up to 20,000 soms or 3 to 7 days of arrest is introduced;
Internal and external migration of SWs;
Frequent change of residence/service points and phone numbers among this key group.

## Slide 9: Programme Preliminary Results_2024_TB
 | Target | Achievement | %
Percentage of TB patients with DST result for at least Rifampicin | 96% | 94,8% | 98,8%
Number of people with confirmed RR-TB and/or MDR-TB notified | 1200 | 729 | 60,8%
Percentage of people with confirmed RR-TB and/or MDR-TB that began second-line treatment | 98% | 94,2% | 96,2%
Percentage of RR/MDR-TB patients with DST results for Fluoroquinolone among the total number of notified RR/MDR-TB patients | 85% | 85,9% | >100%
Treatment success rate of RR/MDR: percentage of patients with RR/MDR successfully treated | 78% | 73,3% | 94%

## Slide 10: Reasons for under achievement of TB indicator:
Number of RR/MDR-TB Cases:
The target for this indicator was set after extensive negotiations during the grant making process: 1200 cases annually. However, the proposed targets were set without taking into account the annual decline of 7.5% (with year-specific declines of 6.3% for 2021-2023, 11.07% for 2022-2023 and finally 5.2% for 2023-2024) and other factors (decline in RR/MDR prevalence among new TB cases, improved treatment success rate, full coverage of FL DST testing, etc.). Therefore, in February-March 2025, UNDP and GF agreed to reduce the targets for 2025-2026 to 7.5%: 1110 for 2026 and 1027 for 2026.

## Slide 11: Project budget Main grant
Description | 2024 | 2025 | 2026 | Total
Non-Health | 5,258,926 | 4,571,063 | 4,855,487 | 14,685,476
Health | 3,244,863 | 5,145,222 | 4,786,191 | 13,176,276
Total | 8,503,789 | 9,716,285 | 9,641,678 | 27,861,752
C19RM
Description | 2024-June 2025
Non-Health | 130,421
Health | 1,467,342
Total | 1,597,763

## Slide 12: Delivery status as of 31 December 2024
Projects | Grant Budget | Expenses | Commit. | Total | Current expenses only | Budget utilization
Effective HIV and TB Control Project in KGZ | 8,503,789 | 6,929,871 | 2,022,681 | 8,952,551 | 82% | 105%
Global Fund COVID-19 Response | 1,115,831 | 413,608 | 836,873 | 1,250,481 | 37% | 112%
TOTAL | 9,619,620 | 7,343,479 | 2,859,554 | 10,203,033 | 76% | 106%

## Slide 13: Delivery status 2021-30 April 2025
Projects | Grant Budget | Expenses | Commit. | Pipeline POs/Expenses | Total | Utilization for Current expenses only | Overall budget utilization
Global Fund COVID-19 Response | 6,624,904 | 5,425,511 | 836,873 | 100,959 | 6,363,343 | 82% | 96%

## Slide 14: Thank you